## Sheet1
SR.NO | PART MASTER- ADD MODE / EDIT MODE |  | 18
| DATE | DESCRIPTION | CATEGORY | REMARK | DEVELOPER'S REMARK
1 | 2020-01-24 | ASSEMBLY OPN RECORDING WITH CHILD PARTS | PART MASTER | CLOSED
2 | 2020-01-24 | MASTER BATCH PERCENTAGE FIELD REQD | PART MASTER | CLOSED
3 | 2020-01-24 | PART LIST ASCENDING ORDER REQD PART NO WISE | PART MASTER | OPEN | OPEN
4 | 2020-01-24 | DATA RESPONSIVENES AFTER MASTER DETAIL UPDATIONS IN SAME ID | PART MASTER | CLOSED
5 | 2020-01-24 | FIELDS DATA EITHER TO BE BLANK / RESET,BASED ON CHRONOLOGY - EDIT MODE IN MB PAGE | PART MASTER | OPEN | OPEN
6 | 2020-01-24 | N/A / DATA ERROR NT HIGHLIGHTED IN POST OPN PAGE | PART MASTER | CLOSED
7 | 2020-01-24 | INTERCHANGE JIGS TO PPC TEXT CHRONO | PART MASTER | CLOSED
8 | 2020-01-24 | CHECK BOX OPTION FOR MULTI CHOICE EG. CUSTOMER | PART MASTER | OPEN | -
9 | 2020-01-24 | OPERATION TYPE ERROR TO BE HIGHLIGHTED BELOW TEXT BOX " SELECT N/A OR TYPE" POP TO BE REMOVED | PART MASTER | CLOSED
10 | 2020-01-24 | PACKAGING TYPE ERROR TO BE HIGHLIGHTED BELOW TEXT BOX " SELECT N/A OR TYPE" POP TO BE REMOVED | PART MASTER | CLOSED
11 | 2020-01-24 | REPLACE MASTER TO DETAILS IN A/E PAGE & DETAILS TO MASTER IN MAIN PG | COMMON | OPEN | CLOSED
12 | 2020-01-24 | NEXT PAGE OPTION REQD FOR MASTER LIST DISPLAYED | ALL MASTER | OPEN | CLOSED
13 | 2020-01-24 | SEARCH OPTION NOT WORKING SEARCH WITH ANY LETTER / WORD | COMMON | CLOSED
14 | 2020-01-24 | LIST DISPLAY 25 PARTS MIN.( MORE THAN 25 PARTS CAN BE ACCOMODATED IF FONT SIZE REDUCED) | LAYOUT | OPEN | CLOSED
15 | 2020-01-24 | LAYOUT & FONTS AS DISCUSSED | LAYOUT | OPEN | PROCESS
16 | 2020-01-24 | AUTOFILED DATA TEXT BOX COLOR CODE REQUIRED | COMMON | OPEN | CLOSED
17 | 2020-01-24 | TEXT CENTRE ALIGN | COMMON | OPEN | CLOSED
18 | 2020-01-24 | CHANGE HEADER TO PBPLASRTIC ERP & WELCOME BOTTOM RIGHT ALIGNMENT | COMMON | CLOSED
19 | 2020-01-24 | CHRONOLOGY OF DATA ENTRY CHK FOR ALL FORMS | COMMON | OPEN | CLOSED
20 | 2020-01-24 | CROSS CHECK NAMES/ TITTLE - PWB | COMMON | OPEN | -
21 | 2020-01-24 | CHANGE CUSTOMER FORM-PWB | CUSTOMER | OPEN | -
22 | 2020-01-24 | WORKERS - SELECTED ACCESS |  | OPEN | PROCESS
23 | 2020-02-21 | WRONG R/M SHOWN IN DP A/G R/M SELECTED | ADD NEW DPR | OPEN | PROCESS
24 | 2020-02-21 | EDIT & DEL FUNCTION REQD | DPR LIST | CLOSED
25 | 2020-02-22 | Value cannot be 0 or less than starting value of shots -48 VALUE ENTERED | ADD NEW DPR | CLOSED
26 | 2020-02-22 | DPR LIST DATE WISE | DPR REPORT | OPEN | CLOSED
27 | 2020-02-26 | ORDER BY MASTERS | COMMON | OPEN | CLOSED
28 | 2020-02-26 | UPDATING IN POST/PACKAGING REQUIRED WHEN PART EDITED | PART MASTER | OPEN | CLOSED
29 | 2020-02-26 | FPA LIST DELETE OPTION | FPA | OPEN | OPEN